## Sheet1
BEFORE THE EVENT
STATUS | OWNER | ACTION ITEM | DUE DATE | NOTES
Not started |  | Determine event type (company retreat, company offsite, incentive trip, meet-ups)
On hold |  | Define your objective (goals + outcomes)
Not started |  | Select a date(s)
Needs action |  | Create a budget + budget sign off
Not started |  | Choose location/venue
Not started |  | Create an event agenda/schedule
Not started |  | Secure travel accommodations (Hotels, flights, transportation, etc.)
Completed |  | EMAIL ¦ Save the date with RSVP to team
In progress |  | EMAIL ¦ Agenda + schedule (include activities, sessions, etc.)
In progress |  | EMAIL ¦ Travel details (venue details, packing checklist, etc.)
Not started |  | EMAIL ¦ Day of reminders (pack list, venue details, etc.)
Not started |  | Check dietary + accesibility requirements
In progress |  | Create Slack channel
In progress |  | Select and book any contractors (speakers, photographers, caterers, etc.)
Not started |  | Prepare session plans/presentations
Not started |  | Design any branded content or swag
Cancelled |  | Order any materials
Not started |  | Choose + book any offsite activities
Pending review |  | Choose + secure any meal accommodations
Not started |  | Brief contractors (speakers, photographers, caterers, etc.)
Not started |  | Hold a walk-through of event space
Not started |  | Create offsite playlist
Not started |  | Arrive early + setup space
DURING THE EVENT
STATUS | OWNER | ACTION ITEM | DUE DATE | NOTES
Not started |  | Ensure necessary equipment and materials are available
On hold |  | Facilitate team-building activities, presentations, and breakout sessions
Not started |  | Manage the schedule and ensure smooth transitions between sessions
Needs action |  | Send updates/announcements to team members
Not started |  | Check in with contractors (speakers, photographers, caterers, etc.)
Not started |  | Capture key insights, ideas, and discussions
AFTER THE EVENT
STATUS | OWNER | ACTION ITEM | DUE DATE | NOTES
In progress |  | EMAIL ¦ Send a post-event survey to gather feedback and insights
Not started |  | Evaluate the success of the event against your objectives
Not started |  | Review participant feedback and document areas for improvement
Not started |  | Share a recap or summary of the event with the team via email or at all-hands
Not started |  | Follow up on action items and next steps identified during the offsite
Not started |  | Incorporate key learnings into future planning and decision-making
Not started |  | EMAIL ¦ Send a "Thank You" email to attendees